## Risks
Risk Register | [10 empty] | Rev A 2/10/23
Last updated:
Next review due:
Status:
Closed
Open
Imminent
[5 empty] | Risk Owners / Managers etc | [7 empty] | Notes: | # (SoS) Start on Site
[5 empty] | Arch | Architect
[5 empty] | SE | Structural Engineers
[5 empty] | PM | Project Manager
[5 empty] | QS | Quantity Surveyors
[5 empty] | MEP | Mechanical & Electrical
[5 empty] | Acoust. | Acoustician
[5 empty] | BC | Building Control
[5 empty] | DT | Design Team
[5 empty] | Dev Co | Development Company
[5 empty] | BT | Charity Build Team
ID | Risk | Consequence or Effect | Mitigation Action / Progress | Risk Owner | Risk Manager | Assistance Required from Team | Risk Importance |  |  | Status | Programme Mitigation Date | Action Code | Risk Evaluation £ Value | Optimistic Assessment % | Optimistic Value £ | Average Assessment % | Average Value £ | Pessimistic Assessment % | Pessimistic Value £ | Notes | Additional Cost were this risk to occur (either before or after action) - £
[7 empty] | Impact | Prob'ty | Rating
Client Risks
1 | Changes to brief at a late stage could endanger programme and lead to extra costs. | Delay project, maybe new planning submission | Strong project team and clear design freeze / sign off and change control process. Client fully briefed. | DT | DT |  | 1 | 1 | 1 | Open | [9 empty] | Design all sorted and agreed
5 | Project delay due to delay in financial approval. | implications to Project Viability |  | BT | PM |  | 3 | 2 | 6 | Open
0
0
0
0
0
0
Design Team Risks
10 | Grants & Gifts | Reduction in funds available | Monitor | BT | BT |  | 3 | 1 | 3 | Open | [9 empty] | Grants will be requested for AV & Kitchen.
0
0
0
0
0
0
0
Financial
26 | Contingency sum not adequate to cover unforseen occurrences. | Project will not be able to proceed | Establish as accurate as possible contingency amount. | BT | PM |  | 3 | 1 | 3 | Open | [9 empty] | Updated figures incorporated into latest cash flow.
0
0
0
0
0
0
0
Contractor Risks
34 | Delay to start on site if tender not agreed. | Additional costs which may effect project viability |  | BT | PM |  | 3 | 2 | 6 | Open | [9 empty] | Meetng with the lowest 3 contractors set up for xxxx
41 | Contractor becomes insolvent. | delays to project whilst replacement contractor procured | Use Contractors who have been vetted for financial robustness. Economic assessment at Tender stage. |  | BT |  | 4 | 2 | 8 | Open | [9 empty] | Financial viability checks made on contractor.
0
0
0
0
0
0
Construction Risks
42 | Site Access issues. Access around the site is very limited. Early contractor involvement required to ensure plant can access the site and construction can be undertaken safely. Impact on constrcution programme and phasing. | If not considered properly will cause severe difficulties when constructing on site. | Define in Contract documents and explain to site users and surrounding neighbours. | BT | PM |  | 3 | 3 | 9 | Open | [9 empty] | Meeting held to ascertain use of private road and agreed for deliveries to help unloading
0
0
0
0
0
0
0
Statutory Risks
52 | The capacity of the existing drainage systems is inadequate to cope with the increased flows arising from the new development. | additional costs and delay to project | Obtain council records on drainage if possible. Idenitfy further CCTV or other necessary investigations. | DT | PM |  | 4 | 3 | 12 | Open | [9 empty] | To be agreed and signed off
0
0
0
0
0
0
0
Health and Safety Risks
0
0
0
0
0
See the 'Scoring' sheet for guidance on Impact and Likelihood assessment.
Note on H26: For guidance see 'Scoring'
Note on I26: For guidance see 'Scoring'
Note on J26: Calculated field

## Scoring
Risk Assessment Scoring
IMPACT | LIKELIHOOD
(1) Insignificant-- Insignificant impact on operations, reputation, or financial condition; no safety or health hazards present. | (1) Low-- Nearly unlikely to happen in the near future and no immediate action is needed.
(2) Mild-- Minimal impact on operations, reputation, or financial condition; minimal safety or health hazards present. | (2) Low-Medium-- Moderately unlikely to happen in the near future and minimal action is needed.
(3) Moderate-- Could delay operations, effect short term programs, require moderate management effort, may draw publicity, minor to moderate safety or health hazards present. | (3) Medium-- Likely to occur and actions should be taken to reduce or control the risk.
(4) Significant-- Significant effect on long-term programs, could result in major property damage, significant financial loss, negative publicity, or cause severe injury. | (4) Medium-High-- More than likely to occur and management or organizers should begin to mitigate.
(5) Catastrophic-- Long-term and serious effect on ability to continue operations, recruit students, staff or faculty, financial support; material breach of confidence and reputation; may result in severe injury and/or death. | (5) High-- High probability the risk will occur; immediate action plans required.

## Instructions
RISK ASSESSMENT INSTRUCTIONS
1. The template is populated with some sample Risks as examples. These should all be deleted before use.
2. Note that the Rating column is calculated and colouring is automated Conditional Formatting.
3. Identify and list all internal and external risks. Identifying these risks includes asking yourself: What could go wrong that would impact your ability to meet your objectives?
4. Note the risks are grouped in sections by Risk Categories.
5. Using the guidance in the Scoring sheet, evaluate the IMPACT and LIKELIHOOD of each identified risk. This may be revised if mitigations are made or circumstances change.
6. Your Rating Score is the IMPACT multiplied by the LIKELIHOOD (3 x 4 = 12). Note: The Risk Score serves as a tool to compare your risks and then prioritize your control efforts.
7. The next step is to determine if you need to do anything, more or less, to reduce or control the risk.
8. Each risk should be costed based on its current impact value. i.e. the Cost that might be incurred if the risk is realised. This might reduce from intial discovery, after mitigations are made and towards the end of the project.